## Tracker
FarmerChat Agentic — UI Components
# | Task | Group | Owner | Status | Start | End | Duration (d) | % Complete
1 | Agent response (SSE stream) | Response | Barry | In progress | 2026-06-04 | 2026-06-20 |  | 30
2 | Clarification component | Response | Barry | In progress | 2026-06-04 | 2026-06-12 |  | 50
3 | Escalation component | Response | Barry | Not started | 2026-06-10 | 2026-06-18 |  | 0
4 | MCP tool call display | Response | Barry | Not started | 2026-06-12 | 2026-06-20 |  | 0
5 | Markdown streaming renderer | Markdown | Barry | In progress | 2026-06-06 | 2026-06-16 |  | 40
6 | Streaming error states | States | Barry | Blocked | 2026-06-14 | 2026-06-20 |  | 0
7 | Integrate into Compose app + PostHog | Integration | Barry | Not started | 2026-06-16 | 2026-06-20 |  | 0
8 | Field testing | Test | Namitha | Not started | 2026-06-22 | 2026-06-26 |  | 0
9 | Handover to engineering | Handover | Barry | Milestone | 2026-06-27 | 2026-06-27 |  | 0
10 | Main release (FC Compose) | Release | Engineering | Not started | 2026-06-30 | 2026-07-17 |  | 0

## Gantt
Gantt — weekly
Task | Owner | Start | End | Status | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13
Agent response (SSE stream) | Barry | 2026-06-04 | 2026-06-20 | In progress
Clarification component | Barry | 2026-06-04 | 2026-06-12 | In progress
Escalation component | Barry | 2026-06-10 | 2026-06-18 | Not started
MCP tool call display | Barry | 2026-06-12 | 2026-06-20 | Not started
Markdown streaming renderer | Barry | 2026-06-06 | 2026-06-16 | In progress
Streaming error states | Barry | 2026-06-14 | 2026-06-20 | Blocked
Integrate into Compose app + PostHog | Barry | 2026-06-16 | 2026-06-20 | Not started
Field testing | Namitha | 2026-06-22 | 2026-06-26 | Not started
Handover to engineering | Barry | 2026-06-27 | 2026-06-27 | Milestone
Main release (FC Compose) | Engineering | 2026-06-30 | 2026-07-17 | Not started

## Dashboard
Dashboard
Total tasks | 10
Weighted % complete
Overdue (past End, not Done)
Weighted by task duration. Updates live on edit.